## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <TRAVEL EVENT SYSTEM>
SB1/US1 | ADMIN | SB1/D1/T1 | Check all information of registered users and activate teir accounts.
|  | SB1/D1/T2 | verify all imags uploaded by contributers(users) and active them.
|  | SB1/D1/T3 | delete all unvaluable data.
SB1/US2 | USER | SB1/D2/T1 | Register Myself Using Gmail ID
|  | SB1/D2/T2 | Receive A Confirmation Mail
|  | SB1/D2/T3 | Login Into The System Using Gmail Id And Password
|  | SB1/D2/T4 | Modify The Account Password
|  | SB1/D2/T5 | retype password
|  | SB1/D2/T6 | forget password
|  | SB1/D2/T7 | verification mail for password
|  | SB1/D2/T8 | link to reset the password
|  | SB1/D2/T9 | reset the password
|  | SB1/D2/T10 | change the password
SB1/US3 | Vsitor | SB1/D3/T1 | send an email for changing the password
|  | SB1/D3/T2 | add the account details
|  | SB1/D3/T3 | edit the account details
|  | SB1/D3/T4 | Register Myself Using Gmail ID
|  | SB1/D3/T5 | Receive A Confirmation Mail
|  | SB1/D3/T6 | Login Into The System Using Gmail Id And Password
|  | SB1/D3/T7 | Modify The Account Password
|  | SB1/D3/T8 | retype password
|  | SB1/D3/T9 | forget password
|  | SB1/D3/T10 | verification mail for password
|  | SB1/D3/T11 | link to reset the password
|  | SB1/D3/T12 | reset the password
|  | SB1/D3/T13 | change the password

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | MANAGE THE TOURS | COMPLETED TH TOURS AND MANGES
2018-09-04 | 180 | 180 | Tasks
2018-09-12 | 120 | 180
2018-09-11 | 80 | 180
2018-09-14 | 56 | 180
2018-09-16 | 15 | 180
2018-09-18 | 5 | 180
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <travel event system>
SB2/US1 | ADMIN |  | Enter the prohibited content
SB2/US2 | USER |  | Add the item and its description
Add the location
add the account details
edit the account details
select the category of images to add
specify the caution money for item
select the added image
select the added iimage
Select the GuideLines
Select the Privacy Policy
Open prohibited images
SB2/US3 | Visitor
Search the near by location
Search the imags and video to download
check the availability of images and videos
download the images
view the downloaded images
view all images
Filter imags according to category
Select the Notifications settings
Select the Help & support
Select the GuideLines
Open prohibited imags
Select the Privacy Policy

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| AJ | ALKA JANGIR
| MS | MEGHA SAMARIYA
| SS | SRISTI SINGH
Verified By:
(Product Owner)

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM
SPRINT 3 - <TRAVEL EVENT SYSTEM>
SB3/US1 | ADMIN |  | view the no of users
apply the opnion mining on review by customers
use dataset for recommendation system
implementation of algorithm for recommendation system
SB3/US2 | Contrebutor(user) |  | specify the discount offers
get the notification
return the caution money
can see the past activity
SB3/US3 | Visitor |  | return the item
select the payment mode
get the notification
can see the past activity
Select the paytm mode for payment
Select the Credit/Debit card mode for payment

## ProductBacklog
PRODUCT BACKLOG
|  |  | Batch 2018_2019 | TRAVEL EVENT SYSTEM
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
SB1 | US1 | User | Can Sign Up if new to the website | User can sign up if new on the website
SB2 | US2 | User | Should provide with the correct personal information to sign up | User should provide with the correct personal information
SB3 | US3 | User | Should confirm the email ID from the confirmation email sent | User should confirm the email id through the confirmation mail
SB4 | US4 | User | Now the new user can check all the products present on the website | User can check all the products present on the website
SB5 | US5 | User | Can login if is a existing user | User can login if is an existing user
SB6 | US6 | User | Can check all the products present on the website | User can check all the products present on the website
SB7 | US7 | User | Update Photo and basic information. | User can viewing his/her profile
SB8 | US8 | User | Password Authentication required. | User can apply the changes in his profile
SB9 | US9 | User | Upload the pictures | User can upload the picture in his profile
SB10 | US10 | User | Upload the videos | User can upload the video in his profile
SB11 | US11 | User | services and cost | User can check the services and cost in his profile
SB12 | US12 | User |  | User can sell and get profit on the old items
SB13 | US13 | User | add the tutorial video | User can learn photography
SB14 | US14 | User | authentication to share personal information | User can secure his personal data
SB15 | US15 | User | to add online learning data | text format learning course will be provided for those who want to learn photography
SB16 | US16 | User | FAQ will help the users to get answers to there questions easily | User will get the answers to their queries through FAQ section easily
SB17 | US17 | User | Users can ask questions in the FAQ sections | User can ask questions in FAQ section as well
SB18 | US18 | User | Users can buy any product from the website | User can buy any product from the website
SB19 | US19 | User | Users can do the payment for the order according to their wish | User can do the payment for the order according to their wish
SB20 | US20 | User | Users can choose pay on delivery option | User can choose pay on delivery option for any product
SB21 | US21 | User | Users can choose net banking payment gateway | User can choose net banking payment gateway
SB22 | US22 | User | Users can choose card payment gateway | User can choose card payment gateway to do the payments
SB23 | US23 | User | To get the refund, users need to provide their account details | User get the refund, but for that users need to provide their account details
SB24 | US24 | User | If a user forgets the password for their account they can change it | User can change the password if they forget the password
SB25 | US25 | User | Security question will help the user to change their password with this option | User can reset the password with the help of the security question
SB26 | US26 | User | User can check all the options related to product | User can check all the options realted to the product
SB27 | US27 | User | User can use the contact us option to ask for any query | User can use the contact us option to ask for any query
SB28 | US28 | User | User can change their personal information | User can change their personal information
SB29 | US29 | User | User can change their mobile number | User can change their mobile number
SB30 | US30 | User | User can add multiple address | User can add multiple address
SB31 | US31 | User | User can check their order history | User can check their order history
SB32 | US32 | User | User ask as many questions as they want | User ask as many questions as they want
SB33 | US33 | User | User can delete their account from the admin panel | User can delete their account
SB34 | US34 | User | Users can not check any others account | User cannot check any others account
SB35 | US35 | User | Users can not delete their comment once done | User can not delete their comment once done
SB36 | US36 | User | Users can not delete their question once asked in FAQ section | User can not delete their question once asked in FAQ section
SB37 | US37 | User | User can check the about option in the website | User can check the about option on the website
SB38 | US38 | User | User can check the meet the team option | User can check the meet the team option on the website
SB39 | US39 | User | Share the location | User can share his location.
SB40 | US40 | Visitor | signup with the gmailid. | I can signup with the account
SB41 | US41 | Visitor | Sign up authentication | I can signup with security
SB42 | US42 | Visitor | sign in with gmail and password | I can log in with gmail id and password.
SB43 | US43 | Visitor | latest wallspaper and newsfeed can be seen | I can see latest photos of the site.
SB44 | US44 | Visitor | Download the images | I can download the images.
SB45 | US45 | Visitor | contact to the photographer | I can contact with the photographer.
SB46 | US46 | Visitor | update the password | I can updtae the password.
SB47 | US47 | Visitor | forgot password | I can forget the password so I can change it.
SB48 | US48 | Visitor | delete the account | I can delete my account
SB49 | US49 | Visitor | payment after the trial version | I can payment for the site.
SB50 | US50 | Visitor | Item purchase. | I can purchase the item.
SB51 | US51 | Visitor | contact to the item seller | I can contact to the item seller.
SB52 | US52 | Visitor | reaction on the photo | I can give reaction on the photo(like symbol of like,love)
SB53 | US53 | Visitor | comment on the photos. | I can comment on the photo.
SB54 | US54 | Visitor | queries to the photographer. | can ask any question to the photographer.
SB55 | US55 | Visitor | profile updation | I can update my profile.
SB56 | US56 | Visitor | video tutorial download | I can download the videos from the site.
SB57 | US57 | Visitor | share the location | I can share my location.
SB58 | US58 | Visitor | see the nearest photographer location. | can see the location of the nearest photographer
SB59 | US59 | Visitor | search the items | can search the items which I want to do
SB60 | US60 | Visitor | search the packages. | search the packages which are availabel on the site
SB61 | US61 | Visitor | search the video | search the videos availabel on the site
SB62 | US62 | Visitor | notification of the videos and photos | received notification of the videos and photos
SB63 | US63 | Visitor | complain for the wrong product | can complain about the wrong product
SB64 | US64 | Visitor | feedback of the product | can give feedback about the product
SB65 | US65 | Visitor | follow the photographers | can follow the photographers on the site
SB66 | US66 | Admin | Managing all the sign's up done by the user | Admin have a record of all the sign's up done by the user
SB67 | US67 | Admin | Managing all the login's done by the user | Admin have a record of all the login's done by the user
SB68 | US68 | Admin | Manages the database for the logined users | Admin can manage the data
SB69 | US69 | Admin | Manage the forget password option for the users | Admin can manage the forget password option
SB70 | US70 | Admin | Sends a confirmation mail when a user sign's up | Admin can send a confirmation mail when any user sign's up
SB71 | US71 | Admin | Won't let a user to login until he confirms the signed up login id | Admin will check for that the user has confirmed the email id or not
SB72 | US72 | Admin | Check the number users online on the website | Admin can check the number users online
SB73 | US73 | Admin | Check the number of hits on the website | Admin can check the number of hits
SB74 | US74 | Admin | Manage the password options | Admin can manage password options
SB75 | US75 | Admin | Manage the inventory panel for the website | Admin can manage the inventory panel for the website
SB76 | US76 | Admin | Add new photographs in the inventory database | Admin can add new photographs in the inventory database
SB77 | US77 | Admin | Delete the unused or unpopular products of the photograph from the database | Admin can delete the unused or unpopular photgraphs from the database
SB78 | US78 | Admin | Manage the discounts given on each photograph shooting. | Admin can manage the discounts given on each photograph session.
SB79 | US79 | Admin | Check if there are more than one active seession of a user | Admin can check if there are more than one active seession of a user
SB80 | US80 | Admin | Delete the suspicious accounts | Admin can delete any suspicious account
SB81 | US81 | Admin | Delete accounts of users who post false information | Admin can delete accounts of users who post false information
SB82 | US82 | Admin | Delete the accouts of users who post nudity | Admin can delete the accouts of users if anything is imprompt
SB83 | US83 | Admin | Check the profit generated each month | Admin can check the profit generated each month
SB84 | US84 | Admin | Stocking of new photographs on the website | Admin can stock new photographs on the website.
SB85 | US85 | Admin | Sending OTP for the payment gateway for netbanking and card payments | Admin can send otp for the payment gateway for netbanking
SB86 | US86 | Admin | The product needs to be managed which a user wants to sell | Admin can manage the products which the users are selling
SB87 | US87 | Admin | All the details should be proper when a user is selling any product | Admin should check that all the information added by the user against the product is correct
SB88 | US88 | Admin | All the comments will be coming to the Admin panel | Admin should check all the comments added by the users
SB89 | US89 | Admin | All the queries asked by the users needs to be managed by the Admin | Admin can check and manage all the queries
SB90 | US90 | Admin | All the queries needs to be answered through the Admin Panel | Admin needs to answer all the queries
SB91 | US91 | Admin | All the answers to the queries will reach the user through email | Admin should answer the query of any user through email
SB92 | US92 | Admin | Can check and edit anything in the comments section | Admin can check and edit any comment
SB93 | US93 | Admin | Can manage the interface given for the users | Admin can manage the interface of the website
SB94 | US94 | Admin | Cares for the site | Admin can take care of the website
SB95 | US95 | Admin | Can add and delete any item on the website | Admin can add and delete any item on the website
SB96 | US96 | Admin | Contact section will be managed by the Admin Panel | Admin can manage the contact sectionon the website
SB97 | US97 | Admin | Can add new developers which are helping the Admin team | Admin can add new developers
SB98 | US98 | Admin | Meet the team panel needs to be managed by the Admin | Admin can manage meet the team panel on the website
SB99 | US99 | Admin | Security of the website | Admin can control the security of the website
SB100 | US100 | Admin | Supports the forget password option | Admin can support the forget password option

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 120 | 120 | Tasks
2018-10-18 | 110 | 120
2018-10-20 | 80 | 120
2018-10-21 | 25 | 120
2018-10-22 | 15 | 120
2018-10-23 | 0 | 120
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Digital College>
SB4/US1 | ADMIN | SB4/D1/T1 | Testing of recommendation system algorithm
|  | SB4/D1/T2 | Testing of whole system
|  | SB4/D1/T3 | Testing of opnion mining algorithm
|  | SB4/D1/T3 | Correcting flawdrawn out while testing
SB4/US2 | LENDOR | SB4/D2/T1 | give feedback about website
|  | SB4/D2/T2 | Receive the feedback from lendee
SB4/US3 | LENDEE | SB4/D3/T1 | Fill the feedback form
|  | SB4/D3/T2 | give feedback about website

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 190 | 190 | Tasks
2019-01-11 | 110 | 190
2019-01-12 | 80 | 190
2019-01-13 | 25 | 190
2019-01-14 | 15 | 190
2019-01-15 | 0 | 190
0
Days